## ProjectData
client_name | consultant_name | company | site_name | project_number | report_title | rap_status | remediation_status_selected | confirmatory_summary_selected | closure_recommendation_selected | conclusions_recommendations | remediation_status | confirmatory_summary | closure_recommendation
Example Energy Ltd. | Ecoventure Inc. | Ecoventure Inc. | Example Wellsite Remediation | REM-2026-001 | Remediation Progress Report | Approved RAP — active | ongoing | not_met | defer | Continue treatment until confirmatory objectives are met for benzene at MW-2. | Remediation activities are ongoing at the site under an approved remedial action plan. This report summarizes confirmatory sampling and progress toward remedial objectives. | Confirmatory sampling results indicate that additional remedial action or monitoring is required for one or more parameters. | Ecoventure recommends deferring closure until additional monitoring or remedial work is completed.

## RemediationObjectives
media | parameter | objective | rap_reference
Groundwater | Benzene | 0.005 mg/L | RAP Table 3-1

## TreatmentEvents
event_date | method | location | volume_m3 | contractor
2026-03-01 | Air sparging | MW-2 vicinity | N/A | Remediation contractor

## ConfirmatorySampling
well_id | sample_date | analyte | result | unit | tier1_limit | Exceedance
MW-2 | 2026-04-15 | Benzene | 0.008 | mg/L | 0.005 | Y

## WasteManifests
manifest_number | waste_type | destination | volume_m3
WM-2026-014 | Impacted soil | Approved facility | 12

## PhraseCatalog
phrase_key | option_id | text
closure_recommendation | support_closure | Based on the data presented, Ecoventure supports proceeding with regulatory closure documentation, subject to agency review.
closure_recommendation | defer | Ecoventure recommends deferring closure until additional monitoring or remedial work is completed.
confirmatory_summary | met | Confirmatory sampling results indicate that remedial objectives were met for the parameters and media evaluated.
confirmatory_summary | not_met | Confirmatory sampling results indicate that additional remedial action or monitoring is required for one or more parameters.
drilling_waste_intro | option_1_aer | Drilling waste was managed in accordance with AER requirements. Option 1 (AER, 2014) applies to this well.
drilling_waste_intro | option_2 | Drilling waste was managed under Checklist Compliance Option 2. Calculation tables are provided in Appendix G.
drilling_waste_intro | option_3 | Drilling waste disposal areas were assessed under Compliance Option 3 per Assessing Drilling Waste Disposal Areas guidance.
drilling_waste_intro | approved_facility | All drilling waste was managed at an AER-approved waste management facility. On-lease DWDA assessment is limited to documentation review.
dwda_salinity_note | equivalent_salinity | Salinity within each drilling waste disposal area may be assessed using Equivalent Salinity Guidelines. Hydrocarbons, metals, and other contaminants within the DWDA and across the remainder of the lease must meet Alberta Tier 1 or Tier 2 remediation guidelines.
dwda_salinity_note | pending_phase2 | Salinity and other contaminants within identified disposal areas require Phase II sampling and comparison to Equivalent Salinity (salinity) and Alberta Tier 1/2 guidelines (other parameters) before reclamation certification.
gw_data_usability | usable | Field notes and laboratory quality control indicate that the groundwater data are suitable for comparison to applicable guidelines, subject to the limitations noted herein.
gw_data_usability | qualified | Some data limitations are noted in the field log and tables below; interpreted trends should be considered qualified where purge volumes or hold times were atypical.
gw_program_intro | annual | This report presents results of the annual groundwater monitoring program conducted to assess groundwater quality and water levels relative to applicable Alberta guidelines and site-specific objectives.
gw_program_intro | baseline | This report summarizes baseline groundwater quality and static water levels following installation of the monitoring well network.
gw_recommendations | continue | Ecoventure recommends continued groundwater monitoring at the established frequency to evaluate temporal trends and confirm stability of exceedances.
gw_recommendations | investigate | Ecoventure recommends additional investigation of exceedances identified in this reporting period, including potential source areas and downgradient wells.
gw_sampling_methods | low_flow | Groundwater samples were collected using low-flow purging and sampling methods in accordance with project-specific sampling procedures and laboratory requirements.
gw_sampling_methods | bailer | Groundwater samples were collected after purging each monitoring well until field parameters stabilized, using dedicated sampling equipment.
phase2_recommendation | recommended | Based on the findings of this Phase I ESA, a Phase II Environmental Site Assessment is recommended to further evaluate identified areas of potential environmental concern.
phase2_recommendation | not_required | Based on the findings of this Phase I ESA, a Phase II Environmental Site Assessment is not recommended at this time, subject to client direction and future land use.
remediation_status | ongoing | Remediation activities are ongoing at the site under an approved remedial action plan. This report summarizes confirmatory sampling and progress toward remedial objectives.
remediation_status | confirmatory | This report documents confirmatory groundwater and soil sampling conducted to verify achievement of remedial objectives.
site_recon_intro | not_completed | A site visit was not completed as part of this Phase I ESA. Findings are based on available records, regulatory databases, and historical air photo review.
site_recon_intro | completed | A site visit was completed as part of this Phase I ESA. Observations from the visit are summarized below and in the site visit checklist.